## Project Mile Stone
| Date | 2023 April | 2023 May | 2023 June | 2023 July | 2023 August | 2023 September | 2023 October | 2023 November | 2023 December | 2024 January | 2024 February | 2024 March
| Project Mile Stone | DCS structure design, function design. | DCS function RFQ and SOW confirm | Discuss MES-DCS message bus (protocol). And message event and format SPEC. | DCS Development coding | DCS Development coding | DCS Development coding | DCS Development coding | 1. DCS - MCS communication test 2. MES-DCS communication test 3. function debug | Integration Test: MES-DCS-MCS
| Check Point | Product | PM Comfirmed Customer approved | PM Tracking | PM Tracking | PM Comfirm | PM Comfirm | PM Comfirm QA test and accept | PM Comfirmed Customer approved | PM Comfirmed Customer approved
| Status | On going | On going
On Going
Finish
Delay
ON
Going